## Recap
First name | Last name | Trigramme | Year | Work tasks | Team tasks | Effectifs
Frame | [5 empty] | 1A | 22
Camille | Simon | CSN | 1A | 0 | 0 | 2A | 0
Come | Archinard | CAD | 1A | 1 | 0 | 3A | 0
Pierre Guillaume | Thomas | PGT | 1A | 0 | 0 | Total | 22
Calixthe | Mattei | CMI | 1A | 4 | 0
Tanguy | Maurin | TMN | 1A | 0 | 0
LAS
Michele | Schio | MSO | 1A | 0 | 0
Victor | Hugo | VDO | 1A | 0 | 0
Paul | Charcaluk | PCK | 1A | 0 | 1
Pierre Emmanuel | Ariaux | PAX | 1A | 0 | 0
Arthur | Delort | ADT | 1A | 0 | 0
Martin | Kasinsky | MKI | 1A | 6 | 1
Engine
Thibault | Lassus | TLS | 1A | 2 | 2
Aimery | Sauliere | ASE | 1A | 2 | 0
Idriss | Gouhaga | IGH | 1A | 0 | 0
Ghassen | Lassoued | GLD | 1A | 4 | 0
Mathieu | Jacquet | MJT | 1A | 2 | 3
Erwan | Benkara | EBA | 1A | 1 | 0
Elec
Arthur | Rodriguez | ARZ | 1A | 6 | 8
Corentin | Lepais | CLS | 1A | 5 | 0
Bruno | Morera | BMA | 1A | 5 | 0
Romain | Martin | RMN | 1A | 1 | 0
Martin | Gomez | MGZ | 1A | 2 | 0

## FSAE
FSAE |  |  |  | Scale |  | Date du jour |  |  | Week
NGO_ARZ |  |  |  | 0 |  | 2017-07-30 |  |  | 31
100
[5 empty] | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14 | W 15 | W 16 | W 17 | W 18 | W 19 | W 20 | W 21 | W 22 | W 23 | W 24 | W 25 | W 26 | W 27 | W 28 | W 29 | W 30 | W 31
Task | Task | First day | Final day | Advancement
FSN
Electronic Throttle Contrôle | ETC |  | 2019-03-15 | 100 | W 11: 100
Impact Attenuator Data | IAD |  | 2019-03-15 | 100 | W 11: 100
Structural Equivalency 3D Model | SE3D |  | 2019-03-15 | 100 | W 11: 100
Structural Equivalency Spreaddheet | SES |  | 2019-03-15 | 100 | W 11: 100
Business Plan Executive Summary | BPES |  | 2019-05-31 | 0 | W 22: 0
Design Spec Sheet | DSS |  | 2019-05-31 | 0 | W 22: 0
Engineering Design Report | EDR |  | 2019-05-31 | 0 | W 22: 0
Magazine Uploads | MU |  | 2019-05-31 | 0 | W 22: 0
Fuel Type Order | FTO |  | 2019-06-14 | 0 | W 24: 0
Team Member Registration Form | TMRF |  | 2019-06-14 | 0 | W 24: 0
Vehicle Status Video | VSV |  | 2019-06-14 | 0 | W 24: 0
Cost Report Ducuments | CRD |  | 2019-06-14 | 0 | W 24: 0
Vehicle arrival on site |  | 2019-07-05 | 2019-07-07 | 0 | W 27: 0; W 28: 0
Vehicle departure |  |  | 2019-07-12 | 0 | W 28: 0
FSATA
Electronic Throttle Contrôle | ETC |  | 2019-03-08 | 100 | W 10: 100
Camping booking form |  |  | 2019-03-08 | 100 | W 10: 100
Preliminary team member list |  |  | 2019-03-08 | 100 | W 10: 100
Fuel system data |  |  | 2019-03-08 | 100 | W 10: 100
Structural Equivalency Spreaddheet | SES |  | 2019-03-20 | 100 | W 12: 100
Camping confirmation and payment |  |  | 2019-04-05 | 0 | W 14: 0
Final team member list |  |  | 2019-05-10 | 0 | W 19: 0
Impact Attenuator Data | IAD |  | 2019-05-31 | 0 | W 22: 0
Engineering Design Report | EDR |  | 2019-06-06 | 0 | W 23: 0
Design Spec Sheet | DSS |  | 2019-06-06 | 0 | W 23: 0
Executive Summary |  |  | 2019-06-06 | 0 | W 23: 0
E-Cost Report |  |  | 2019-06-21 | 0 | W 25: 0
E_BOM |  |  | 2019-06-21 | 0 | W 25: 0
Vehicle Status Video | VSV |  | 2019-06-26 | 0 | W 26: 0
Change of Faculty Advisor |  |  | 2019-06-28 | 0 | W 26: 0
Vehicle Shipping and Delivery |  |  | 2017-07-23 | 0 | W 30: 0
Vehicle Shipping and Collection |  |  | 2019-07-30 | 0 | W 31: 0
Formulas:
Week = WEEKNUM([Date du jour])

## Team
Team | Department leaders |  | Scale |  | Date du jour |  |  | Week
MJT_ARZ_TLS | DL |  | 0 |  | 2019-03-11 |  |  | 11
100
|  |  |  | W 8 |  | W 9 |  | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
RollOut
Communication flyer | ARZ |  | 75 |  | 50 | 75 | 75 | 75 | 75 | 75
Press file | TLS | [5 empty] | 50 | 95 | 95 | 95
Force alpha +
P12P | PCK |  | 50 | [7 empty] | 10 | 50 | 50
Profession de foi | MJT | ARZ | 100 |  |  |  | 100
Create Slack | MJT |  | 100 | [6 empty] | 50 | 100
Create Git | MJT |  | 50 | [6 empty] | 0 | 50 | 50 | 50
Create EPSABox | TLS |  | 50 | [6 empty] | 50 | 50 | 50 | 50
Create Brainstorming slides | ARZ |  | 100 | [6 empty] | 50 | 100
Team meeting
CR 13/30/2019 | MKI |  | 0 | [7 empty] | 0
TOPs
Set Top Projet date | ARZ |  | 0 | [7 empty] | 0 | 0
Prepare TOP Projet | ARZ |  | 0 | [8 empty] | 0
Define specification document | ARZ |  | 0 | [8 empty] | 0
Budget | DL | [11 empty] | 0
TOPs previsionnal dates | ARZ | DL | [10 empty] | 0
Prepare RVP2 | DL |  | 20 | [7 empty] | 20 | 20 | 20
RVP2 reports | DL | [9 empty] | 20 | 20 | 20
RVP2 slides | DL | [9 empty] | 20 | 20 | 20
Templates
Prepare life recap template | ARZ |  | 90 | [7 empty] | 90 | 90
Formulas:
Week = WEEKNUM([Date du jour])

## Frame
Frame |  |  | Scale |  | Date du jour |  | Week
CMI_PTS_TMN_CAD_CSN |  |  | 0 |  | 2019-03-07 |  | 10
100
|  |  |  | W 8 |  | W 9 | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
Pushbar
Finish the pushbar design | CAD |  | 80 |  |  |  | 20 | 20 | 40 | 40 | 80 | 80
Main car design
Define the main frame variables | CMI | [7 empty] | 0 | 0
Define the specification points | CMI | [7 empty] | 0 | 0
Translate the competition objective as specification poitns | CMI | [7 empty] | 0 | 0
Define the variables values for the specification documents | CMI | [7 empty] | 0 | 0
Formulas:
Week = WEEKNUM([Date du jour])

## LAS
LAS |  |  | Scale | Date du jour | Date du jour |  | Week
MKI_PAX_VDO_PCK_MSO_ADT |  |  | 0 |  | 2019-03-07 |  | 10
100
|  |  |  | W 8 |  | W 9 | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
Tyre data
Find tyre data | MKI | [6 empty] | 0 | 0 | 0 | 0 | 0
Tyre model | MSO | [9 empty] | 30 | 30
Main car design
Define the main LAS variables | MKI | [8 empty] | 0
Define the specification points | MKI | [8 empty] | 0
Translate the competition objective as specification poitns | MKI | [8 empty] | 0
Use Skidpad models to have specification values | MKI | [8 empty] | 0
Use Optimum lap to have specification values | IGH | [7 empty] | 0 | 0 | 0 | 0
Compare | MKI | IGH | [6 empty] | 0 | 0 | 0 | 0
Models and correlation
Longitudinal acceleration model (2 wheels)
Longitudinal acceleration model (4 wheels)
How to use Optimus data to improve the model (sensors, ...)
Brake model (2 wheels)
Brake model (4 wheels)
How to use Optimus data to improve the model (brake pressure sensors, ...)
Lateral acceleration model (2 wheels)
Lateral acceleration model (4 wheels)
How to use Optimus data to improve the model (sensors, ...)
Skid pad model (2 wheels)
Skid pad model (4 wheels)
How to use Optimus data to improve the model (acceleration sensors, tyre temp ? ...)
Maximum turn radius
Minimum turn radius
Anti roll bar model
How to use Optimus data to improve the model (roll data with and without anti-roll bar, ...)
Formulas:
Week = WEEKNUM([Date du jour])

## Engine
Engine |  |  | Scale |  | Date du jour |  | Week
MJT_TLS_EBA_IGH_ASE |  |  | 0 |  | 2019-03-07 |  | 10
100
|  |  |  | W 8 |  | W9 | W 10 |  | W 11 |  | W 12
Task | Trigramm | Trigramm | Advancement
General Model
Optimum lap | IGH |  | 20 |  |  |  | 20 | 20 | 20
Main car design
Define the main drivetrain variables | ASE |  | 0 | [5 empty] | 0
Define the specification points | ASE |  | 0 | [5 empty] | 0
Translate the competition objective as specification poitns | ASE |  | 0 | [5 empty] | 0
Use acceleration models to have specification values | ASE |  | 0 | [5 empty] | 0
Use Optimum lap to have specification values | IGH |  | 0 | [5 empty] | 0 | 0 | 0 | 0
Compare | ASE | IGH | 0 | [5 empty] | 0 | 0 | 0 | 0
Air intake
Measure intake manufolds | TLS |  | 0
Measure exhaust manufolds | TLS |  | 0
Exhaust system
Measure intake manufolds | MJT |  | 0
Measure exhaust manufolds | MJT |  | 0
Cooling
Thermodynamic and thermal model | ASE |  | 0
Surface and Fan consumption | ASE
Fuel system
Look at what is done in Nascar | GLD |  | 0 |  |  |  | 0 | 0
See how we can do it with our rules | GLD |  | 0 | [5 empty] | 0 | 0
Refueling | GLD |  | 0 | [7 empty] | 0 | 0
Under and overpressure issues | GLD |  | 0
Secondary transmission
Load cases on excentric carriers | EBA |  | 0
Formulas:
Week = WEEKNUM([Date du jour])

## Elec
Electronic |  |  | Scale |  | Date du jour |  |  | Week
ARZ_CLS_BMA_MGZ_RMN |  |  | 0 |  | 2019-03-26 |  |  | 13
100
|  |  |  | W 8 |  | W9 |  | W 10 |  | W 11 |  | W 12 |  | W 13 |  | W 14
Task | Trigramm | Trigramm | Advancement
Shifter
Finish the shifter soft | BMA | CLS | 100 |  |  |  | 100
Connect to the shifter | BMA | CLS | 100 |  |  |  |  | 100 | 100
Finish 2 rear cards | BMA | CLS | 0 |  |  |  |  | 0 | 0 | 0 | 0
Test the shifter soft with atomix | BMA | CLS | 0 | [8 empty] | 0 | 0 | 0 | 0
BSPD | BMA | CLS
Front card
Pinout File |  |  | 20 |  |  |  |  | 20 | 20
Program the error display | MGZ |  | 100 |  |  |  | 100
Test error display | ARZ |  | 100 | [7 empty] | 0 | 0 | 0 | 100
Finish the comments of the soft | MGZ |  | 100 |  |  |  | 50 | 50 | 50 | 100 | 100
Test the final program | ARZ |  | 100 | [6 empty] | 50 | 50 | 50 | 50 | 100
Finish cards x2 |  |  | 30 |  |  |  |  | 20 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Test handmade cards |  |  | 20 | [5 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Dashboard
Test 2nd dashboard | ARZ |  | 100 |  |  |  | 100
Steering Wheel
Paddle shifter design | RMN
Sensors
Contact FLE for sensor callibration | ARZ |  | 0 | [8 empty] | 0 | 0
Change the connectors | ARZ |  | 0
Select sensors with each departements | ARZ
Formulas:
Week = WEEKNUM([Date du jour])